## Project Overview
Regional Vehicle Sales Analysis – Project Overview
Project ID | 33
Project Title | Regional Vehicle Sales Analysis
Domain | Automobile
Type | Data Science / EDA Project
Duration | 3 Weeks (Sprint 1: Days 1-7 ¦ Sprint 2: Days 8-14 ¦ Sprint 3: Days 15-21)
Tech Stack | Python, Pandas, NumPy, Matplotlib, Seaborn
Goal | Analyze region-wise vehicle sales data across India to identify demand patterns, high-growth markets, segment performance, and generate actionable insights for OEMs, dealers, or policymakers.

## Epics & Stories
Regional Vehicle Sales Analysis – Epics, Stories & Tasks
Issue Key | Type | Epic / Story / Task | Description | Sprint | Priority | Story Points | Status | Start Date | Due Date
RVSA-E1 | EPIC | Project Framing & Requirement Analysis | Define project objectives, scope, key business questions, and success criteria for the Regional Vehicle Sales Analysis. | 1 | High | - | To Do | 2026-04-08 | 2026-04-11
RVSA-S1 | STORY | Define Project Objectives & Scope | As a student analyst, I want to clearly define what the project will analyse, why it matters, and the boundaries (in-scope/out-of-scope) so that the analysis stays focused. | 1 | High | 3 | To Do
RVSA-T1 | TASK | Write project objective statement | Draft a one-paragraph objective covering: what is being analysed, the domain context, and intended audience (OEMs, dealers, policymakers). | 1 | High | 1 | To Do
RVSA-T2 | TASK | Define in-scope and out-of-scope items | List: states/UTs covered, vehicle segments (2W, 3W, 4W, LCV, HCV), time range, and what is excluded (pricing, supply chain, international data). | 1 | High | 1 | To Do
RVSA-S2 | STORY | Identify Key Business Questions | As a student analyst, I want a structured list of 6–8 business questions the analysis will answer, grouped by category, so that EDA and visualizations are goal-directed. | 1 | High | 2 | To Do
RVSA-T3 | TASK | Draft business questions (regional demand) | Write 2 questions on which states lead in sales volume and which are growing fastest. | 1 | High | 1 | To Do
RVSA-T4 | TASK | Draft business questions (segment & trends) | Write 2 questions on segment mix by region and YoY growth trends. Write 1 question on OEM market share by state. | 1 | High | 1 | To Do
RVSA-S3 | STORY | Define Success Criteria & Deliverables | As a student, I want documented success criteria and a clear list of final deliverables so that I know exactly what constitutes a complete submission. | 1 | Medium | 2 | To Do
RVSA-T5 | TASK | List success criteria | Define: all business questions answered with data evidence, minimum 3 insights per category, reproducible notebook, charts covering regional and temporal views. | 1 | Medium | 1 | To Do
RVSA-T6 | TASK | List final deliverables | Document required outputs: Jupyter notebook, project report (4–6 pages), PPT (10–12 slides), and conclusions document. | 1 | Medium | 1 | To Do
RVSA-E2 | EPIC | Dataset Selection & Environment Setup | Identify and download a suitable vehicle sales dataset (SIAM/Vahan/Kaggle), create a data dictionary, and set up the Python project environment. | 1 | High | - | To Do | 2026-04-08 | 2026-04-11
RVSA-S4 | STORY | Identify & Download Dataset | As a data analyst, I want to evaluate available India vehicle sales datasets and select the most complete and reliable one so that analysis is built on quality data. | 1 | High | 3 | To Do
RVSA-T7 | TASK | Research datasets on SIAM, Vahan, Kaggle, data.gov.in | Compare available datasets on: state/UT coverage, year range, segment breakdown, file format, and completeness. | 1 | High | 2 | To Do
RVSA-T8 | TASK | Download selected dataset and verify file | Download the chosen CSV/Excel file. Confirm it opens correctly and matches the expected schema. | 1 | High | 1 | To Do
RVSA-S5 | STORY | Create Data Dictionary | As a data analyst, I want a documented data dictionary for every column in the dataset so that all team members and evaluators understand the data. | 1 | High | 2 | To Do
RVSA-T9 | TASK | Document all columns with name, type, description, example | For each column: column name, data type (int/str/date), description, example value, known issues. | 1 | High | 1 | To Do
RVSA-T10 | TASK | Note data sources and coverage gaps | Document the original data source URL, year range covered, which states or segments may be missing. | 1 | Medium | 1 | To Do
RVSA-S6 | STORY | Set Up Python Environment & Folder Structure | As a developer, I want a clean virtual environment and organized project folder so that the project is reproducible and submission-ready. | 1 | High | 2 | To Do
RVSA-T11 | TASK | Create virtual environment and install libraries | Set up venv or conda. Install: pandas, numpy, matplotlib, seaborn, jupyter, openpyxl. | 1 | High | 1 | To Do
RVSA-T12 | TASK | Create project folder structure | Folders: /data/raw, /data/clean, /notebooks, /outputs/charts, /reports. Add README.md. | 1 | High | 1 | To Do
RVSA-E3 | EPIC | Data Ingestion & Quality Checks | Load the dataset into Python, validate schema and data types, then check for missing values, duplicates, and inconsistencies. | 1 | High | - | To Do | 2026-04-12 | 2026-04-14
RVSA-S7 | STORY | Load Data & Validate Schema | As a data engineer, I want to load the dataset into a Pandas DataFrame and validate its schema so that downstream analysis works on correctly-typed data. | 1 | High | 2 | To Do
RVSA-T13 | TASK | Load CSV/Excel with pandas and inspect | Use pd.read_csv() or pd.read_excel(). Print shape, column names, dtypes, and first 5 rows. | 1 | High | 1 | To Do
RVSA-T14 | TASK | Cast incorrect column data types | Convert year columns to int, sales columns to numeric, state/segment columns to string. Fix date columns. | 1 | High | 1 | To Do
RVSA-S8 | STORY | Data Quality Assessment | As a data analyst, I want to identify all quality issues (nulls, duplicates, inconsistencies) so that the cleaning phase has a documented plan. | 1 | High | 3 | To Do
RVSA-T15 | TASK | Check missing values across all columns | Run isnull().sum(). Document percentage missing per column. Flag any column with >20% missing. | 1 | High | 1 | To Do
RVSA-T16 | TASK | Check for duplicate rows | Run duplicated().sum(). Inspect duplicates. Document count and decide: drop or keep. | 1 | High | 1 | To Do
RVSA-T17 | TASK | Check categorical inconsistencies | Audit state names, segment labels. Identify mismatches like 'Maharashtra' vs 'MH'. Check numerics for negatives or zeroes. | 1 | High | 1 | To Do
RVSA-E4 | EPIC | Data Cleaning & EDA | Clean and preprocess the dataset systematically, then perform exploratory data analysis and summarize insights per business question. | 2 | High | - | To Do | 2026-04-15 | 2026-04-18
RVSA-S9 | STORY | Clean & Preprocess Dataset | As a data engineer, I want a fully clean, standardized dataset saved to /data/clean so that all analysis is built on consistent, reliable data. | 2 | High | 3 | To Do
RVSA-T18 | TASK | Impute or drop missing values | Apply strategy per column: drop rows with missing sales data; impute categorical columns with mode if <5% missing. | 2 | High | 1 | To Do
RVSA-T19 | TASK | Standardize state and segment names | Create a mapping dictionary. Apply str.replace() or map() to normalize all state and segment labels. | 2 | High | 1 | To Do
RVSA-T20 | TASK | Remove duplicates and save clean file | Drop exact duplicate rows. Save final clean DataFrame to /data/clean/rvsa_clean.csv. | 2 | High | 1 | To Do
RVSA-S10 | STORY | Perform Exploratory Data Analysis | As a data analyst, I want to explore distributions, correlations, and regional patterns so that I can answer all 6–8 business questions with evidence. | 2 | High | 5 | To Do
RVSA-T21 | TASK | Univariate EDA: distributions and summary stats | Histograms for sales volume. Bar charts for unique states and segments. Print min, max, mean, median for numeric columns. | 2 | High | 2 | To Do
RVSA-T22 | TASK | Bivariate EDA: sales by state and segment | Grouped bar charts: top 10 states by total sales. Stacked bar: segment mix per region. Heatmap: state x segment sales. | 2 | High | 2 | To Do
RVSA-T23 | TASK | Temporal EDA: YoY sales trends | Line chart: national total sales per year. Line chart: segment-wise YoY trend. Identify peak and trough years. | 2 | High | 1 | To Do
RVSA-E5 | EPIC | Feature Engineering & Visualization & Storytelling | Create derived KPI metrics, engineer new features, then build final visualizations and construct the data narrative. | 2 | High | - | To Do | 2026-04-19 | 2026-04-22
RVSA-S11 | STORY | Engineer Derived Metrics & KPIs | As a data analyst, I want to create calculated columns (YoY growth, market share, CAGR) so that the analysis goes beyond raw sales numbers to actionable KPIs. | 2 | High | 3 | To Do
RVSA-T24 | TASK | Calculate YoY growth % per state per segment | Formula: (current_year - prev_year) / prev_year * 100. Add as new column. | 2 | High | 1 | To Do
RVSA-T25 | TASK | Calculate market share % per state | Formula: state_sales / national_total * 100 per year. Add as new column. | 2 | High | 1 | To Do
RVSA-T26 | TASK | Calculate 3-year CAGR and segment rank per state | CAGR formula. Also add a dominant_segment column showing the top-selling segment per state per year. | 2 | Medium | 1 | To Do
RVSA-S12 | STORY | Build Final Visualizations | As a student, I want polished, labelled charts saved to /outputs/charts so that they are ready to embed in the report and PPT. | 2 | High | 3 | To Do
RVSA-T27 | TASK | Create regional sales bar/map chart | Horizontal bar chart: top 15 states by total sales volume. Label each bar with value and rank. | 2 | High | 1 | To Do
RVSA-T28 | TASK | Create segment mix stacked bar chart | Stacked bar: segment breakdown (2W/3W/4W/LCV/HCV) for top 10 states. Use consistent color palette. | 2 | High | 1 | To Do
RVSA-T29 | TASK | Create YoY trend line chart and growth heatmap | Line chart: national YoY trend per segment. Heatmap: state x year with sales volume as color intensity. | 2 | High | 1 | To Do
RVSA-S13 | STORY | Build Data Story & Insight Narrative | As a student, I want a structured insight narrative mapped to each business question so that the report and PPT tell a clear, evidence-backed story. | 2 | High | 2 | To Do
RVSA-T30 | TASK | Write 2–3 sentence insight per business question | For each of the 6–8 questions: reference the chart, state the key finding, quantify it (e.g. 'Maharashtra accounts for 22% of 4W sales'). | 2 | High | 1 | To Do
RVSA-T31 | TASK | Identify top 3 overall strategic insights | Synthesize cross-question findings into 3 headline insights suitable for the executive summary of the report. | 2 | Medium | 1 | To Do
RVSA-E6 | EPIC | Advanced Analysis, Validation & Final Submission | Optionally apply ML/statistical techniques, validate all results with sanity checks, and prepare the final notebook, report, PPT and conclusions. | 3 | High | - | To Do | 2026-04-23 | 2026-04-28
RVSA-S14 | STORY | Advanced Analysis (Optional) | As a student analyst, I want to apply ML or statistical techniques (forecasting, clustering) to enhance the analysis if time permits. | 3 | Low | 3 | To Do
RVSA-T32 | TASK | Apply KMeans clustering to group states by sales profile | Use sklearn KMeans on state-level features (total sales, growth rate, segment share). Plot clusters. | 3 | Low | 2 | To Do
RVSA-T33 | TASK | Apply linear regression for sales forecasting | Predict next 1–2 years of national sales using sklearn LinearRegression on historical trend. | 3 | Low | 1 | To Do
RVSA-S15 | STORY | Validate Results & Sanity Checks | As a student, I want to cross-verify all key numbers against known industry benchmarks so that findings are credible and defensible. | 3 | High | 2 | To Do
RVSA-T34 | TASK | Cross-verify top states against known facts | Confirm Maharashtra tops 4W, UP/Tamil Nadu top 2W — compare against SIAM published summaries. | 3 | High | 1 | To Do
RVSA-T35 | TASK | Verify all YoY % calculations manually on 3 samples | Manually compute 3 YoY growth values. Confirm they match DataFrame output. Check for off-by-one year errors. | 3 | High | 1 | To Do
RVSA-S16 | STORY | Finalize Notebook & Write Report | As a student, I want a clean, end-to-end Jupyter notebook and a professional report so that the project is ready for evaluation. | 3 | High | 3 | To Do
RVSA-T36 | TASK | Clean and structure Jupyter notebook | Remove debug cells. Add markdown section headers. Ensure notebook runs top-to-bottom without errors. | 3 | High | 1 | To Do
RVSA-T37 | TASK | Write project report (4–6 pages) | Sections: Objective, Dataset, Methodology, Findings per question, Limitations, Conclusions. Embed charts. | 3 | High | 2 | To Do
RVSA-S17 | STORY | Create PPT & Final Submission | As a student, I want a 10–12 slide PPT and all files packaged for submission so that the project is complete. | 3 | High | 3 | To Do
RVSA-T38 | TASK | Build PPT (10–12 slides) | Slides: Title, Objective, Dataset, Methodology, 4–5 insight slides with charts, Conclusion, Limitations. | 3 | High | 2 | To Do
RVSA-T39 | TASK | Final review and submit all files | Review notebook, report, PPT for consistency. Submit as per teacher's instructions. Archive project folder. | 3 | High | 1 | To Do

## Sprint Plan
Regional Vehicle Sales Analysis – Sprint Plan (3 Weeks)
Sprint 1 – Days 1 to 7: Foundation, Framing & Data Setup
Issue Key | Story / Task | Priority | Story Points | Status | Phase
RVSA-S1 | Define Project Objectives & Scope | High | 3 | To Do | Story
RVSA-T1 | Write project objective statement | High | 1 | To Do | Task
RVSA-T2 | Define in-scope and out-of-scope items | High | 1 | To Do | Task
RVSA-S2 | Identify Key Business Questions | High | 2 | To Do | Story
RVSA-T3 | Draft business questions (regional demand) | High | 1 | To Do | Task
RVSA-T4 | Draft business questions (segment & trends) | High | 1 | To Do | Task
RVSA-S3 | Define Success Criteria & Deliverables | Medium | 2 | To Do | Story
RVSA-T5 | List success criteria | Medium | 1 | To Do | Task
RVSA-T6 | List final deliverables | Medium | 1 | To Do | Task
RVSA-S4 | Identify & Download Dataset | High | 3 | To Do | Story
RVSA-T7 | Research datasets on SIAM, Vahan, Kaggle | High | 2 | To Do | Task
RVSA-T8 | Download selected dataset and verify file | High | 1 | To Do | Task
RVSA-S5 | Create Data Dictionary | High | 2 | To Do | Story
RVSA-T9 | Document all columns | High | 1 | To Do | Task
RVSA-T10 | Note data sources and coverage gaps | Medium | 1 | To Do | Task
RVSA-S6 | Set Up Python Environment & Folder Structure | High | 2 | To Do | Story
RVSA-T11 | Create virtual environment and install libraries | High | 1 | To Do | Task
RVSA-T12 | Create project folder structure | High | 1 | To Do | Task
RVSA-S7 | Load Data & Validate Schema | High | 2 | To Do | Story
RVSA-T13 | Load CSV/Excel with pandas and inspect | High | 1 | To Do | Task
RVSA-T14 | Cast incorrect column data types | High | 1 | To Do | Task
Sprint 2 – Days 8 to 14: Cleaning, EDA & Features
Issue Key | Story / Task | Priority | Story Points | Status | Phase
RVSA-S8 | Data Quality Assessment | High | 3 | To Do | Story
RVSA-T15 | Check missing values | High | 1 | To Do | Task
RVSA-T16 | Check for duplicate rows | High | 1 | To Do | Task
RVSA-T17 | Check categorical inconsistencies | High | 1 | To Do | Task
RVSA-S9 | Clean & Preprocess Dataset | High | 3 | To Do | Story
RVSA-T18 | Impute or drop missing values | High | 1 | To Do | Task
RVSA-T19 | Standardize state and segment names | High | 1 | To Do | Task
RVSA-T20 | Remove duplicates and save clean file | High | 1 | To Do | Task
RVSA-S10 | Perform Exploratory Data Analysis | High | 5 | To Do | Story
RVSA-T21 | Univariate EDA: distributions and summary stats | High | 2 | To Do | Task
RVSA-T22 | Bivariate EDA: sales by state and segment | High | 2 | To Do | Task
RVSA-T23 | Temporal EDA: YoY sales trends | High | 1 | To Do | Task
RVSA-S11 | Engineer Derived Metrics & KPIs | High | 3 | To Do | Story
RVSA-T24 | Calculate YoY growth % | High | 1 | To Do | Task
RVSA-T25 | Calculate market share % | High | 1 | To Do | Task
RVSA-T26 | Calculate 3-year CAGR and segment rank | Medium | 1 | To Do | Task
Sprint 3 – Days 15 to 21: Visualize, Validate & Submit
Issue Key | Story / Task | Priority | Story Points | Status | Phase
RVSA-S12 | Build Final Visualizations | High | 3 | To Do | Story
RVSA-T27 | Create regional sales bar/map chart | High | 1 | To Do | Task
RVSA-T28 | Create segment mix stacked bar chart | High | 1 | To Do | Task
RVSA-T29 | Create YoY trend line chart and growth heatmap | High | 1 | To Do | Task
RVSA-S13 | Build Data Story & Insight Narrative | High | 2 | To Do | Story
RVSA-T30 | Write insight per business question | High | 1 | To Do | Task
RVSA-T31 | Identify top 3 overall strategic insights | Medium | 1 | To Do | Task
RVSA-S14 | Advanced Analysis (Optional) | Low | 3 | To Do | Story
RVSA-T32 | KMeans clustering of states | Low | 2 | To Do | Task
RVSA-T33 | Linear regression for sales forecasting | Low | 1 | To Do | Task
RVSA-S15 | Validate Results & Sanity Checks | High | 2 | To Do | Story
RVSA-T34 | Cross-verify top states against benchmarks | High | 1 | To Do | Task
RVSA-T35 | Verify YoY calculations on 3 samples | High | 1 | To Do | Task
RVSA-S16 | Finalize Notebook & Write Report | High | 3 | To Do | Story
RVSA-T36 | Clean and structure Jupyter notebook | High | 1 | To Do | Task
RVSA-T37 | Write project report (4–6 pages) | High | 2 | To Do | Task
RVSA-S17 | Create PPT & Final Submission | High | 3 | To Do | Story
RVSA-T38 | Build PPT (10–12 slides) | High | 2 | To Do | Task
RVSA-T39 | Final review and submit all files | High | 1 | To Do | Task